## 1. Project Manager
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 1 - Project Manager (Project Lead)
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | In consultation with the Contracting Authority, prepare the Schedule of Services for all suppliers to be appointed by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Facilitate regular meetings in order to progress Design and Pricing information, consult and liaise with the Lead Designer, Cost Manager and Principal Designer in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Identify activities to be undertaken and responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake and take responsibility for actions to be undertaken by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers and in accordance with the Schedule of Services for each, the Project Roles Table, the Design Responsibility Matrix and the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall confirm the actions agreed in writing with the supplier(s) and copy to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Manage, co-ordinate and participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Organise workshops and exercises and manage contributions of other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Provide recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Organise meetings with the Contracting Authority, Project Lead, Lead Designer, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | In conjunction with the other suppliers and subject to the specific duties pursuant to each respective Call Off Agreement and/or Building Contract, make all necessary arrangements with planning, local and other statutory bodies to enable the Project to proceed to completion and handover. Arrange for, co-ordinate and pursue all necessary applications required in connection with relevant statutory or regulatory bodies, highway authorities and (if applicable) river and waterway authorities. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.1 | Assist with the submission of documentation to landlords and/or funding bodies and/or any third parties who have an interest in the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Establish and maintain project management procedures, hierarchy of responsibility, the Communication Strategy and the exchange of information both informally and formally at Information Exchanges. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Manage the Change Control Procedures and monitor Design and Cost Information development against the Site Information, Project Information, Project Budget, Design Programme, Project Programme and the risk register. Ensure that any difficulties are rectified and the approved Project Budget and Project Programme are not adversely impacted. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.13 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.14 | Check and authorise applications for payment from the Project Design Team; maintain a fee drawdown register | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Discuss options with the Contracting Authority for the assembly of the Project Team and assist the Contracting Authority to assemble and appoint the Project Team | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Collate comments and facilitate workshops to discuss the Business Case and to develop the Strategic Brief for the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Review findings from post project evaluations from relevant projects and and lead and manage the Sustainability Checkpoint to inform the approach to the Strategic Definition for the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.5 | Draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation and Brief
3.1 | Develop the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Contracting Authority Business Case, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Review Site Information and Project Information and collate comments from and facilitate workshops to develop the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | In consultation with the Project Team and the Contracting Authority, agree the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Prepare the Project Roles Table and Contractual Tree and continue to assist the Contracting Authority to assemble and appoint the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Agree with the Lead Designer the Design Responsibility Matrix, Information Exchange and Technology Strategy, all prepared by the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Prepare option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventiation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Prepare the Feasibility Study for the Contracting Authority preferred option(s). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Review and update the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Prepare the Handover Strategy, commence Risk Assessments in preparation for the Concept Design stage, lead and manage the Sustainability Checkpoint, and develop the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.1 | Monitor and review progress and performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.11 | Select one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Monitor preparation and progress of the Concept Design and preliminary Cost Information. Ensure all the foregoing are in accordance with the Initial Project Brief, Design Responsibility Matrix, Information Exchanges and the Design Programme. Prepare Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Review Site Information, Project Information and collate and agree changes to the Initial Project Brief and prepare and issue the Final Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Prepare the Sustainability Strategy and the Maintenance and Operational Strategy and lead and manage the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Review and develop the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Prepare the initial Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Review and update the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Review and update the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Agree with the Lead Designer the Design Responsibility Matrix, Information Exchange and Technology Strategy, all prepared by the Lead Designer. Agree the preliminary Cost Information, prepared by the Cost Manager. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Select and prepare a list of tenderers with the Contracting Authority. |  | ✓ | ✓ |  | ✓ | ✓
4.1 | Collate information from the Project Team and assemble the Employer’s Requirements. |  | ✓ | ✓ |  | ✓ | ✓
4.11 | Collate and issue the tender documentation. |  | ✓ | ✓ |  | ✓ | ✓
4.12 | Lead the assessment of the tenders and prepare the tender report. The assessment should include the review and evaluation of the alignment of the design and specification, pricing and cash-flow, health and safety information, programmes and method statements etc in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. The Supplier shall lead the evaluation and review of the programmes and method statements. |  | ✓ | ✓ |  | ✓ | ✓
4.13 | Agree the detailed content and assist with the finalisation of the contract documentation (for pre-construction activities). |  | ✓ | ✓ |  | ✓ | ✓
4.14 | Verify that the Contractor has all required insurances, collateral warranties, bonds etc in place. |  | ✓ | ✓ |  | ✓ | ✓
4.15 | Monitor and review progress and performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
RIBA Stage 3 - Developed Design
5.1 | Review and comment on the preparation and progress of the Developed Design, Site Information, Project Information and Cost Information to ensure it is developed in accordance with the Project Strategies, Design Responsibility Matrix, Information Exchanges and the Design Programme and Project Budget. | ✓ |  | ✓
5.2 | Review and update the Sustainability Strategy and the Maintenance and Operational Strategy and lead and manage the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Review and update the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Review and update the Construction Strategy and Health and Safety Strategy | ✓ |  | ✓
5.5 | Review and update the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Review and update the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Agree with the Lead Designer the Design Responsibility Matrix, Information Exchange and Technology Strategy, all prepared by the Lead Designer. Agree the Cost Information, prepared by the Cost Manager. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Manage the Change Control Procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Select and prepare a list of tenderers with the Contracting Authority. | ✓
5.1 | Collate information from the Project Team and assemble the Employer’s Requirements. | ✓
5.12 | Collate and issue the tender documentation. | ✓
5.13 | Lead the assessment of the tenders and prepare the tender report. The assessment should include the review and evaluation of the alignment of the design and specification, pricing and cash-flow, health and safety information, programmes and method statements etc in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. The Supplier shall lead the evaluation and review of the programmes and method statements. | ✓
5.14 | Agree the detailed content and assist with the finalisation of the contract documentation (for pre-construction activities). | ✓
5.15 | Verify that the Contractor has all required insurances, collateral warranties, bonds etc in place. | ✓
5.16 | Lead the assessment of the submission from the selected tenderer of designs and specifications, pricing information and cash-flows, health and safety information, programmes and method statements etc to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. The Supplier shall lead the evaluation and review of the programmes and method statements. |  | ✓ |  | ✓ | ✓ | ✓
5.17 | Monitor and review the performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Review and comment on the preparation and progress of the Technical Design, Site Information, Project Information and Cost Information to ensure it is developed in accordance with the project Strategies, Design Responsibility Matrix, Information Exchanges and the Design Programme and Project Budget. |  |  | ✓
6.2 | Review and update the Sustainability Strategy and the Maintenance and Operational Strategy and lead and manage the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Review and update the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Review and update the Construction Strategy and the Health and Safety Strategy. | ✓ |  | ✓
6.5 | Review and update the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Review and update the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Agree with the Lead Designer the Design Responsibility Matrix, Information Exchange and Technology Strategy, all prepared by the Lead Designer. Agree the Cost Information, prepared by the Cost Manager. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Manage the Change Control Procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Select and prepare a list of tenderers with the Contracting Authority. |  |  | ✓
6.10 | Collate information from the Project Team and assemble the Employer’s Requirements. |  |  | ✓
6.11 | Collate and issue the tender documentation. |  |  | ✓
6.12 | Lead the assessment of the tenders and prepare the tender report. The assessment should include the review and evaluation of the alignment of the design and specification, pricing and cash-flow, health and safety information, programmes and method statements etc in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. The Supplier shall lead the evaluation and review of the programmes and method statements. |  |  | ✓
6.13 | Agree the detailed content and assist with the finalisation of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.14 | Verify that the Contractor has all required insurances, collateral warranties, bonds etc in place. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.15 | Lead the assessment of the submission from the selected tenderer of designs and specifications, pricing information and cash-flows, health and safety information, programmes and method statements etc to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. The Supplier shall lead the evaluation and review of the programmes and method statements. | ✓ | ✓ |  | ✓ | ✓ | ✓
6.16 | Monitor and review the performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Manage the review of construction standards to verify conformance with the contract documentation Health and Safety strategies, Design Programme and Construction Programme and that all site queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Manage the review of the development of the design to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all Design Queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Manage the provision of information to the Contract Administrator to assist administration of the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Review and update the Sustainability Strategy and lead the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Manage the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Review and update the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Review and update the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Agree with the Lead Designer the Information Exchange, prepared by the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Manage the review of proposals for the testing, setting to operation and commissioning and the witnessing of all testing and commissioning and that all testing and commissioning records are present and accurate and reflect the required performance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Prepare a planned maintenance programme for the project, post handover, and provide recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Monitor and review the performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Manage the handover of the building in accordance with the Handover Strategy and manage and prepare the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Manage the provision of information to the Contract Administrator to assist administration of the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Manage the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Manage the update of the As Constructed Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Manage the completion of the tasks in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Manage and prepare the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Manage the update of As Constructed information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Manage the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Manage the post completion defect rectification process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Manage the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Manage and prepare the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 2. Architect
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 2 - Architectural Services
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend regular meetings in order to progress Design, consult and liaise with the Lead Designer in the preparation and development of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake the required activities and take responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Co-operate at all times with the Principal Designer and provide Design Information and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Attend meetings with the Contracting Authority, Project Lead, Lead Designer, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | In conjunction with the other suppliers and subject to the specific duties pursuant to each respective Call Off Agreement and/or Building Contract, assist the Project Lead to make all necessary arrangements with planning, local and other statutory bodies to enable the Project to proceed to completion and handover. Assist the Project Lead to arrange for, co-ordinate and pursue all necessary applications required in connection with relevant statutory or regulatory bodies, highway authorities and (if applicable) river and waterway authorities. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Assist the Project Lead with the submission of documentation to landlords and/or funding bodies and/or any third parties who have an interest in the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Participate in the Change Control Procedures and monitor Design development against the Site Information, Project Information, Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Review findings from post project evaluations from relevant projects and contribute to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.5 | Discuss the Project with the appropriate planning authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Discuss the Project with the appropriate planning authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Contribute to the development of the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Review Site Information and Project Information and provide comments and attend workshops, as required, to assist the development of the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Contribute to the development of the Project Roles Table and Contractual Tree. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Provide comment to the Lead Designer to prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Contribute to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventilation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Contribute to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Review and contribute to the update of the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Contribute to the preparation of the Handover Strategy, prepare Risk Assessments in preparation for the Concept Design stage and contribute to the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.11 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3a.1 | Carry out a full site inspection/site survey of any existing fabric, finishings, fittings etc, and make recommendations for, any specialist investigations or surveys which may be necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Liaise with planning authorities as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Prepare the architectural Concept Design in accordance with the Initial Project Brief and Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Undertake third party consultations and any Research and Development as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Incorporate agreed changes to the Concept Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Contribute to the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Contribute to the development of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Contribute to the Construction Strategy and the development of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.10 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.11 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.12 | Contribute to the selection of a list of tenderers. |  | ✓ | ✓ |  | ✓ | ✓
4.13 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ | ✓ |  | ✓ | ✓
4.14 | Contribute to the preparation of the tender documentation |  | ✓ | ✓ |  | ✓ | ✓
4.15 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ | ✓ |  | ✓ | ✓
4.16 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ | ✓ |  | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Liaise with planning authorities as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Submit planning application to the appropriate planning authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Prepare the architectural Developed Design in accordance with the Final Project Brief, Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. Contribute to the development of Project Strategies. | ✓ |  | ✓
5.4 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Incorporate agreed changes to the Developed Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.10 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.11 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.12 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.13 | Contribute to the selection of a list of tenderers. | ✓
5.14 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.15 | Contribute to the preparation of the tender documentation | ✓
5.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Submit the Building Regulations application. |  |  | ✓
6.2 | Prepare the architectural Technical Design in accordance with the Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. |  |  | ✓
6.3 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Incorporate agreed changes to the Technical Design, Site Information and Project Information in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Contribute to the review and update of the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.1 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.11 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.12 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.13 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.14 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.15 | Contribute to the preparation of the tender documentation |  |  | ✓
6.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.17 | Assist in the agreement of the detailed content and the finalisation of the contract documetation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any clarifications from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Review standards of construction to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all site queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Review development of the design to verify conformance with the contract documentation, Health and Safety strategies, Design Programme, Information Exchanges and the Construction Programme and that all Design Queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Contribute, as necessary, to the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Contribute to the review and update of the Sustainability Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Contribute to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Monitor and verify that agreed changes to the Design during Construction are implemented in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.10 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Review proposals for the testing, setting to operation and commissioning of all building fabric, walls, partitions, doors, equipment and fittings etc. Witness all testing and commissioning and check that all testing and commissioning records are present and accurate and reflect the required performance. Identify to the Lead Designer incomplete and/or innaccurate information and/or testing and commissioning that evidences the required performance is not being achieved. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.14 | Prepare the 'As Constructed' Information. |  |  | ✓
7a.1 | Make recommendations for sample-taking and the carrying out of specialist inspection tests of materials and workmanship. Following approval of recommendations for testing, arrange for the inspections and tests to be undertaken and examine the results of such tests whether on or off site. In liaison with the Lead Designer take any necessary action to ensure that any deficiencies are rectified. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | Make recommendations for the opening of work to determine that it is generally in accordance with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.3 | Visit the sites of fabrication and assembly to inspect such materials or workmanship before delivery to site. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.4 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.5 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Provide the Lead Designer with the defects list. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Undertake the tasks in accordance with the Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Contribute to the provision of information to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Contribute to the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Contribute to the update of the 'As Constructed' Information. | ✓ | ✓ |  | ✓ | ✓ | ✓
8.6 | Update the 'As Constructed' Information. |  |  | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL requirements. Identify all outstanding defects and notify the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 3. Cost Consultant
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 3 - Cost Management Services
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend regular meetings in order to progress the Cost Information, consult and liaise with the Project Lead in the preparation and development of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Identify activities to be undertaken and responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake and take responsibility for actions to be undertaken by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Co-operate at all times with the Principal Designer and provide information and Risk Assessments as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Attend meetings with the Contracting Authority, Project Lead, Lead Designer, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Participate in the Change Control Procedure and monitor development of the Cost Information against the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Review findings from post project evaluations from relevant projects and contribute to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Lead and manage the contribution in respect of budgetary considerations to the development of the Initial Project Brief and prepare the Project Budget. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Review Site Information and Project Information and provide comments and attend workshops, as required, to assist the development of the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Provide comment for the development of the Project Roles Table and Contractual Tree by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Provide comment to the Project Lead and Lead Designer for the preparation of the Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Lead and manage the Cost Information contribution to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventiation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Lead and manage the Cost Information contribution to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Contribute to the update of the Project Programme. Lead and manage the update of the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Contribute to the preparation of the Handover Strategy and Risk Assessments in preparation for Concept Design stage and contribute to the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Prepare the preliminary Cost Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Update the preliminary Cost Information and the Project Budget for the agreed changes to the Concept Design, Site Information and Project Information in compliance with the Change Control Procedures and the Information Exchanges and contribute to the production of the Final Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Contribute to the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Contribute to the development of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Contribute to the Construction Strategy and the development of the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Contribute to the review and update of the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.10 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.11 | Contribute to the preparation of the tender documentation. |  | ✓ |  | ✓ | ✓ | ✓
4.12 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of all pricing and cash-flow information in each of the Contractor's Proposlas with the Employer's Requirements set out in the tender documentation. and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.13 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Update the preliminary Cost Information and the Project Budget for the agreed changes to the Developed Design, Site Information and Project Information in compliance with the Change Control Procedures and the Information Exchanges and contribute to the production of the Final Project Brief. | ✓ |  | ✓
5.2 | Contribute to the development of the Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Contribute to the review and update of the Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Contribute to the selection of a list of tenderers. | ✓
5.10 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.11 | Contribute to the preparation of the tender documentation | ✓
5.12 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of all pricing and cash-flow information in each of the Contractor's Proposlas with the Employer's Requirements set out in the tender documentation. and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.13 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.14 | Lead the assessment of the submission from the selected tenderer of pricing information and cash-flows, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any clarifications from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Update the Cost Information and the Project Budget for the agreed changes to the Technical Design, Site Information and Project Information in compliance with the Change Control Procedures and the Information Exchanges and contribute to the production of the Final Project Brief. |  |  | ✓
6.2 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Contribute to the review and update of the Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.9 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.10 | Contribute to the preparation of the tender documentation |  |  | ✓
6.11 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of all pricing and cash-flow information in each of the Contractor's Proposlas with the Employer's Requirements set out in the tender documentation. and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.12 | Assist in the agreement of the detailed content and the finalisation of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.13 | Lead the assessment of the submission from the selected tenderer of pricing information and cash-flows, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any clarifications from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Contribute, as necessary, to the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Attend regular progress meetings with the Contractor and other members of the Project Team and provide ongoing advice on the overall cost of the project in relation to the Project Budget and recommend any corrective action that may be necessary. Undertake valuations of the works in accordance with the provisions of the Building Contract and provide cashflow updates to the Project Lead and the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | In consultation with the Contracting Authority and the Project Team, ensure that rigorous cost control is undertaken in accordance with Change Control Procedures and provide estimates of cost in connection therewith and negotiate the costs of approved changes with the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Visit the site at such intervals as are necessary in order to be fully aware of all matters which could affect the cost of the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Produce financial statements at monthly intervals, or at such other intervals as shall be agreed with the Contracting Authority that demonstrate the current financial position of the project and a forecast of the cost at completion and submit to the Project Lead and the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Contribute to the review and update of the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Contribute to the review and update of the Sustainability Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.10 | Contribute to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | In consultation with the Contracting Authority and the Project Team, contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Lead the assessment of the submission from the selected tenderer of pricing information and cash-flows, to ensure alignment with the contract documentation and the further review and evaluation of responses to any clarifications from the tenderer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.14 | Alert the the Project Lead, the Contract Administrator and the Contracting Authority other members of the Project Team to the possibility of receiving claims from the Contractor. If such claims are submitted, advise the Project Lead and the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.1 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor.
7a.2 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Undertake tasks listed in Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Agree the final account, or equivalent, in accordance with the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Provide a detailed statement of final cost to the Contracting Authority, Project Lead and Contract Administrator. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Contribute to the provision of information to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.6 | Contribute to the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the post completion defect rectification process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 4. Structural Engineer
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 4 - Civil and Structural Engineer Services
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend regular meetings in order to progress Design, consult and liaise with the Lead Designer in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake the required activities and take responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Co-operate at all times with the Principal Designer and provide Design Information and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Attend meetings with the Contracting Authority, Project Lead, Lead Designer, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | In conjunction with the other suppliers and subject to the specific duties pursuant to each respective Call Off Agreement and/or Building Contract, assist the Project Lead to make all necessary arrangements with planning, local and other statutory bodies to enable the Project to proceed to completion and handover. Assist the Project Lead to arrange for, co-ordinate and pursue all necessary applications required in connection with relevant statutory or regulatory bodies, highway authorities and (if applicable) river and waterway authorities. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Assist the Project Lead with the submission of documentation to landlords and/or funding bodies and/or any third parties who have an interest in the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Participate in the Change Control Procedures and monitor Design development against the Site Information, Project Information, Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Review findings from post project evaluations from relevant projects and contribute to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Contribute to the development of the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Review Site Information and Project Information and provide comments and attend workshops, as required, to assist the development of the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Contribute to the development of the Project Roles Table and Contractual Tree. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Provide comment to the Lead Designer to prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Contribute to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventilation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Contribute to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Review and contribute to the update of the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Contribute to the preparation of the Handover Strategy and Risk Assessments in preparation for the Concept Design stage and contribute to the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3a.1 | Arrange for the carrying out of any geotechnical or other investigations that may be necessary, interpret the results in liaison with the Project Team and make recommendations to the Contracting Authority. Undertake any further interpretation that may be necessary in order to submit further recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3a.2 | Carry out a full site inspection/site survey of any existing fabric, finishings, fittings etc, and make recommendations for, any specialist investigations or surveys which may be necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Prepare the civil and structural engineering Concept Design in accordance with the Initial Project Brief and Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Undertake third party consultations and any Research and Development as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Incorporate agreed changes to the Concept Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Contribute to the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Contribute to the development of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Contribute to the Construction Strategy and the development of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.10 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.11 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.12 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.13 | Contribute to the preparation of the tender documentation |  | ✓ |  | ✓ | ✓ | ✓
4.14 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.15 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Liaise with planning authorities as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Assist in the submission of the planning application to the appropriate planning authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Prepare the civil and structural engineering Developed Design in accordance with the Final Project Brief, Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. Contribute to the development of Project Strategies. | ✓ |  | ✓
5.4 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Incorporate agreed changes to the Developed Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.10 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.11 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.12 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.13 | Contribute to the selection of a list of tenderers. | ✓
5.14 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.15 | Contribute to the preparation of the tender documentation | ✓
5.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Assist with the submission of the Building Regulations application. |  |  | ✓
6.2 | Prepare the civil and structural engineering Technical Design in accordance with the Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. |  |  | ✓
6.3 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Incorporate agreed changes to the Technical Design, Site Information and Project Information in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Contribute to the review and update of the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.10 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.11 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.12 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.13 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.14 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.15 | Contribute to the preparation of the tender documentation |  |  | ✓
6.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Review standards of construction to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all site queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Review development of the design to verify conformance with the contract documentation, Health and Safety strategies, Design Programme, Information Exchanges and the Construction Programme and that all Design Queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Contribute, as necessary, to the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Contribute to the review and update of the Sustainability Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Contribute to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Monitor and verify that agreed changes to the Design during Construction are implemented in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.1 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Review proposals for the testing, setting to operation and commissioning of all civil and structural engineering work. Witness all testing and commissioning and check that all testing and commissioning records are present and accurate and reflect the required performance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.14 | Prepare the 'As Constructed' Information. |  |  | ✓
7a.1 | Make recommendations for sample-taking and the carrying out of specialist inspection tests of materials and workmanship. Following approval of recommendations for testing, arrange for the inspections and tests to be undertaken and examine the results of such tests whether on or off site. In liaison with the Lead Designer take any necessary action to ensure that any deficiencies are rectified. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | Make recommendations for the opening of work to determine that it is generally in accordance with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.3 | Visit the sites of fabrication and assembly to inspect such materials or workmanship before delivery to site. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.4 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.5 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Provide the Lead Designer with the defects list. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Undertake the tasks in accordance with the Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Contribute to the provision of information to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Contribute to the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Contribute to the update of the 'As Constructed' Information. | ✓ | ✓ |  | ✓ | ✓ | ✓
8.6 | Update the 'As Constructed' Information. |  |  | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL requirements. Identify all outstanding defects and notify the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 5. Building Services
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 5 - Building Services Engineer
| Ref | Scope of Services | Procurement Type
|  |  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
| 1 | General Services
| 1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.2 | Attend regular meetings in order to progress Design, consult and liaise with the Lead Designer in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake the required activities and take responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.6 | Co-operate at all times with the Principal Designer and provide Design Information and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.7 | Attend meetings with the Contracting Authority, Project Lead, Lead Designer, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.8 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.9 | In conjunction with the other suppliers and subject to the specific duties pursuant to each respective Call Off Agreement and/or Building Contract, assist the Project Lead to make all necessary arrangements with planning, local and other statutory bodies to enable the Project to proceed to completion and handover. Assist the Project Lead to arrange for, co-ordinate and pursue all necessary applications required in connection with relevant statutory or regulatory bodies, highway authorities and (if applicable) river and waterway authorities. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.10 | Assist the Project Lead with the submission of documentation to landlords and/or funding bodies and/or any third parties who have an interest in the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.11 | Participate in the Change Control Procedures and monitor Design development against the Site Information, Project Information, Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 1.12 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
i | 2 | RIBA Stage 0 - Strategic Definition
| 2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 2.2 | Review findings from post project evaluations from relevant projects and contribute to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3 | RIBA Stage 1 - Preparation & Brief
| 3.1 | Consult with planning authorities, building control authorities, fire authorities, environmental health authorities and public utility authorities to assess the availability and capacity of existing mechanical and electrical services and advise the Client on any infrastructure or upgrade of such services that are deemed inadequate. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.2 | Contribute to the development of the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.3 | Review Site Information and Project Information and provide comments and attend workshops, as required, to assist the development of the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.4 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.5 | Contribute to the development of the Project Roles Table and Contractual Tree. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.6 | Provide comment to the Lead Designer to prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.7 | Contribute to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventilation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.8 | Contribute to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.9 | Review and contribute to the update of the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.10 | Contribute to the preparation of the Handover Strategy and Risk Assessments in preparation for the Concept Design stage and contribute to the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3.11 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 3a.1 | Carry out a full site inspection/site survey of any existing fabric, finishings, fittings etc, and make recommendations for, any specialist investigations or surveys which may be necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4 | RIBA Stage 2 - Concept Design
| 4.1 | Prepare the building services engineering Concept Design in accordance with the Initial Project Brief and Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.2 | Consult with planning authorities, building control authorities, fire authorities, environmental health authorities and public utility authorities, undertake third party consultations and any Research and Development as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.3 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.4 | Incorporate agreed changes to the Concept Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.5 | Contribute to the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.6 | Contribute to the development of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.7 | Contribute to the Construction Strategy and the development of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.8 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.9 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.10 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 4.11 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
| 4.12 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
| 4.13 | Contribute to the preparation of the tender documentation |  | ✓ |  | ✓ | ✓ | ✓
| 4.14 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
| 4.15 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
| 4a.1 | Conduct any necessary negotiations with the public utility authorities relating to services connections, sub-stations, existing services, services diversions and similar matters. |  | ✓ |  | ✓ | ✓ | ✓
| 5 | RIBA Stage 3 - Developed Design
| 5.1 | Consult with planning authorities, building control authorities, fire authorities, environmental health authorities and public utility authorities as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.2 | Assist with the submission of the planning application to the appropriate planning authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.3 | Prepare the building services engineering Developed Design in accordance with the Final Project Brief, Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. Contribute to the development of Project Strategies. | ✓ |  | ✓
| 5.4 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.5 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.6 | Incorporate agreed changes to the Developed Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.7 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.8 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.9 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.1 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.11 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.12 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 5.13 | Contribute to the selection of a list of tenderers. | ✓
| 5.14 | Contribute to the preparation of the Employer’s Requirements. | ✓
| 5.15 | Contribute to the preparation of the tender documentation | ✓
| 5.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
| 5.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
| 5.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
| 5a.1 | Conduct any necessary negotiations with the public utility authorities relating to services connections, sub-stations, existing services, services diversions and similar matters. | ✓
| 6 | RIBA Stage 4 - Technical Design
| 6.1 | Assist with the submission of the Building Regulations application. |  |  | ✓
| 6.2 | Prepare the building services engineering Technical Design in accordance with the Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. |  |  | ✓
| 6.3 | Undertake third party consultations as required. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.4 | Assist the Lead Designer with preparation of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.5 | Incorporate agreed changes to the Technical Design, Site Information and Project Information in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.6 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.7 | Contribute to the review and update of the Handover Strategy and Design Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.8 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.9 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.10 | Contribute to the review and update of the Design Programme, Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.11 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.12 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.13 | Contribute to the selection of a list of tenderers. |  |  | ✓
| 6.14 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
| 6.15 | Contribute to the preparation of the tender documentation |  |  | ✓
| 6.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
| 6.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 6.18 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation (for pre-construction activities) and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
| 6a.1 | Conduct any necessary negotiations with the public utility authorities relating to services connections, sub-stations, existing services, services diversions and similar matters. |  |  | ✓
| 7 | RIBA Stage 5 - Construction
| 7.1 | Review standards of construction to verify conformance with the contract documentation, Health and Safety strategies, Design Programme Information Exchanges and the Construction Programme and that all site queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.2 | Review development of the design to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all Design Queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.3 | Contribute, as necessary, to the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.4 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.5 | Contribute to the review and update of the Sustainability Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.6 | Contribute to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.7 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.8 | Contribute to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.9 | Monitor and verify that agreed changes to the Design during Construction are implemented in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.10 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.11 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.12 | Review proposals for the testing, setting to operation and commissioning of all building engineering services plant and equipment etc. Witness all testing and commissioning and check that all testing and commissioning records are present and accurate and reflect the required performance. Identify to the Lead Designer incomplete and/or innaccurate information and/or testing and commissioning that evidences the required performance is not being achieved. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.13 | In consultation with the Contracting Authority and the Project Team, contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7.14 | Prepare the 'As Constructed' Information. |  |  | ✓
| 7a.1 | Make recommendations for sample-taking and the carrying out of specialist inspection tests of materials and workmanship. Following approval of recommendations for testing, arrange for the inspections and tests to be undertaken and examine the results of such tests whether on or off site. In liaison with the Lead Designer take any necessary action to ensure that any deficiencies are rectified. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7a.2 | Make recommendations for the opening of work to determine that it is generally in accordance with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7a.3 | Visit the sites of fabrication and assembly to inspect such materials or workmanship before delivery to site. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7a.4 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 7a.5 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 8 | RIBA Stage 6 - Handover & Close-Out
| 8.1 | Confirm to the Lead Designer if the performance criteria for all elements of the building services design have been achieved and provide the Lead Designer with the defects list. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 8.2 | Undertake the tasks in accordance with the Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 8.3 | Contribute to the provision of information to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 8.4 | Contribute to the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 8.5 | Contribute to the update of the 'As Constructed' Information. | ✓ | ✓ |  | ✓ | ✓ | ✓
| 8.6 | Update the 'As Constructed' Information. |  |  | ✓
| 9 | RIBA Stage 7 - In-Use
| 9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.5 | Contribute to the post completion defect rectification process in accordance with GSL requirements. Identify all outstanding defects and notify the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.6 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
| 9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 6. Lead Designer
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 6 - Lead Designer
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Facilitate regular meetings in order to progress Design, consult and liaise with the Project Lead in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Identify activities to be undertaken and responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake and take responsibility for actions to be undertaken by the Lead Designer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Monitor and expedite the activities of those undertaking Design to maintain progress in accordance with the Design Programme and the Project Programme. Review, develop and update the Design Programme for the Project Lead’s approval. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Establish rigorous design management procedures to monitor the production of Design information in order that any shortcomings and/or queries are immediately highlighted and rectified in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy, Design Programme and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers and in accordance with the Schedule of Services for each, the Project Roles Table, the Design Responsibility Matrix and the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Where there is duplication between the Services provided by the Supplier under the term and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Co-operate at all times with the Principal Designer in respect of the provision of Design Information and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | In conjunction with the other suppliers and subject to the specific duties pursuant to each respective Call Off Agreement and/or Building Contract, assist the Project Lead to make all necessary arrangements with planning, local and other statutory bodies to enable the Project to proceed to completion and handover. Assist the Project Lead to arrange for, co-ordinate and pursue all necessary applications required in connection with relevant statutory or regulatory bodies, highway authorities and (if applicable) river and waterway authorities. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Assist the Project Lead with the submission of documentation to landlords and/or funding bodies and/or any third parties who have an interest in the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.13 | Comply with the project management procedures, hierarchy of responsibility, the Communication Strategy and the exchange of information both informally and formally at Information Exchanges. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.14 | Participate in the Change Control Procedures and monitor and validate Design development against the Site Information, Project Information, Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.15 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Review findings from post project evaluations from relevant projects and lead the contribution in respect of design to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Obtain information on ownership and any leases of the site(s), Site Information including any existing buildings on the site, boundaries, any known easements, underground services, rights of way, rights of support and other relevant matters and advise the Project Team and the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Request approval for site surveys, investigations etc to develop the Site Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Lead and manage the contribution in respect of design to the development of the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Review Site Information and Project Information and provide comments and attend workshops, as required, to develop the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Lead and manage the comment in respect of design for the development of the Project Roles Table and Contractual Tree by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Agree with the Project Lead and prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Lead and manage the design contribution to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventilation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Lead and manage the design contribution to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Review and contribute to the update of the Project Budget and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.11 | Lead and manage the design contribution to the preparation of the Handover Strategy, preparation of Risk Assessments in preparation for the Concept Design stage, the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.12 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.13 | Monitor and review the performance of suppliers undertaking design. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Lead and manage the production of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Lead and manage the production of the Concept Design in accordance with the Initial Project Brief and Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Review Site Information, Project Information and collate and agree changes in respect of design for the Final Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Manage the incorporation and co-ordination of agreed changes to the Concept Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Lead and manage the contribution for design in the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Lead and manage the contribution in respect of design in the review and development of the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Lead and manage the contribution in respect of design for the Construction Strategy and the development of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Lead and manage the contribution in respect of design in the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Lead and manage the contribution in respect of design in the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.10 | Lead and manage the contribution in respect of design for the preparation of the preliminary Cost Information, Project Strategies and Final Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.11 | Agree with the Project Lead and prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.12 | Manage the Information Exchange requirements | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.13 | Manage the identification of the requirement for specialist designers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.14 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.15 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.16 | Contribute to the preparation of the tender documentation. |  | ✓ |  | ✓ | ✓ | ✓
4.17 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.18 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
4.19 | Monitor and review the performance of suppliers undertaking design. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Lead and manage the production of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Lead and manage the review and update of the Developed Design in accordance with the Design Programme. Contribute to the development of Project Strategies. | ✓ |  | ✓
5.3 | Manage the incorporation and co-ordination of agreed changes to the Developed Design, Site Information and Project Information in compliance with the Change Control Procedures, Project Strategies, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ |  | ✓
5.4 | Lead and manage the contribution for design in the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and lead and manage the contribution for design for the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Lead and manage the contribution in respect of design in the review and update of the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Lead and manage the contribution in respect of design in the review and update of the Construction Strategy and contribute to the review and update of the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Lead and manage the contribution in respect of design in the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Lead and manage the contribution in respect of design in the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Agree with the Project Lead and prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.10 | Manage the Information Exchange requirements | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.11 | Manage the identification of the requirement for specialist designers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.12 | Contribute to the selection of a list of tenderers. | ✓
5.13 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.14 | Contribute to the preparation of the tender documentation. | ✓
5.15 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.16 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.17 | Lead the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
5.18 | Monitor and review the performance of the suppliers undertaking design. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Lead and manage the production of the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.2 | Lead and manage the review and update of the Technical Design in accordance with the Project Strategies, Design Responsibility Matrix, Information Exchange and the Design Programme. |  |  | ✓
6.3 | Manage the incorporation and co-ordination of agreed changes to the Technical Design, Site Information and Project Information in compliance with the Change Control Procedures, Design Responsibility Matrix, Information Exchanges and the Design Programme. |  |  | ✓
6.4 | Lead and manage the contribution for design in the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and lead and manage the contribution for design for the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Lead and manage the contribution in respect of design in the review and update of the Handover Strategy and Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Lead and manage the contribution in respect of design in the review and update of the Construction Strategy and contribute to the review and update of the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Lead and manage the contribution in respect of design in the review and update the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Lead and manage the contribution in respect of design in the review and update the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Agree with the Project Lead and prepare the Information Exchange . | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.10 | Manage the Information Exchange requirements | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.11 | Manage the identification of the requirement for specialist designers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.12 | Liaise with specialist sub-contractors as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.13 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.14 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.15 | Contribute to the preparation of the tender documentation |  |  | ✓
6.16 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.17 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.18 | Lead the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
6.19 | Monitor and review the performance of the suppliers undertaking design. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Lead and mange the review of standards of construction to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all site queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Lead and manage the review of the development of the design to verify conformance with the contract documentation, Health and Safety strategies, Design Programme and Construction Programme and that all Design Queries are resolved in accordance with the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Lead and manage the contribution in respect of design, as necessary, for the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Lead and manage the contribution in respect of design to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Lead and manage the contribution in respect of design to the review and update of the Sustainability Strategy and lead the contribution in respect of design for the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Lead and manage the contribution in respect of design to the review and update of the Construction Strategy and the Health and Safety Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Lead and manage the contribution in respect of design to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Lead and manage the contribution in respect of design to monitor and verify that agreed changes to the Design during Construction are implemented in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchange, Technology Strategy and Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.10 | Manage and co-ordinate witnessing of the testing and commissioning. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Manage the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Liaise with specialist suppliers as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.14 | Manage the preparation of the 'As Constructed' Information. |  |  | ✓
7.15 | Monitor and review the performance of the suppliers undertaking design. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.1 | Make recommendations for sample-taking and the carrying out of specialist inspection tests of materials and workmanship. Following approval of recommendations for testing, arrange for the inspections and tests to be undertaken and examine the results of such tests whether on or off site. In liaison with the Lead Designer take any necessary action to ensure that any deficiencies are rectified. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | Make recommendations for the opening of work to determine that it is generally in accordance with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.3 | Visit the sites of fabrication and assembly to inspect such materials or workmanship before delivery to site. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.4 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.5 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Provide the Contract Administrator and Project Lead with the aggregated defects list. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Manage the tasks in respect of the design in accordance with the Handover Strategy and lead the contribution in respect of design for the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Manage the provision of information from the designers to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Manage the update from the designers of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Manage the update from the designers of the 'As Constructed' Information. | ✓ | ✓ |  | ✓ | ✓ | ✓
8.6 | Manage the update the 'As Constructed' Information. |  |  | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Manage the tasks in respect of design listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Manage the contribution in respect of design to the Post Occupancy Evaluation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Manage the contribution in respect of design to the update of 'As Constructed' information in accordance with Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Manage the contribution in respect of design to the update of Project Information in response to ongoing Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Manage the contribution in respect of design to the post completion defect rectification process in accordance with GSL. requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Manage the contribution in respect of design to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Manage the contribution in respect of design to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
*

## 7. Client Adviser
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 7 - Client Adviser
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend meetings with the Client, Project Lead, other suppliers and Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Participate in the Change Control Procedure and monitor Design and Cost Information development against the Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Review and comment on the Business Case, other core project requirements and the Strategic Brief and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Provide recommendations to the the Contracting Authority for the assembly of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Review and comment on the findings from post project evaluations and the Sustainability Checkpoint that are being used to inform the approach to the Strategic Definition for the Project and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Review and comment on the Project Brief, the Initial Project Budget and the Project Programme and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.5 | Review and comment on the Project Execution Plan and provide recommedations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Review the development of the Initial Project Brief including Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and other parameters or constraints. Provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Provide recommendations to the Contracting Authority for the assembly of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Review and comment on the Site Information, Project Information and the initial Project Brief and provide recommendation to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Review and comment on the procurement route and standard form of Building Contract and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Review and comment on the Project Roles Table and Contractiual Tree and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Review and comment on the Design Responsibility Matrix, information Exchange and Technology Strategy and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Review and comment on the options appraisal and provide recommendation to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Review and comment on the Feasibility Study and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Review and comment on the Project Budget and Project Programme and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Review and comment on the Handover Strategy, the Sustainability Check Point and the Project Execution Plan and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.11 | Provide comment to the Contracting Authoity on the performance of the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.12 | Review proposals for the selection of one or more specialists, to provide input into option appraisals and/or the Feasibility Study and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Review and comment on the preparation and progress of the Concept Design, Site Information, Project Information, preliminary Cost Information and Project Strategies and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Review and comment on the Final Project Brief and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Review and comment on the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Review and comment on the Handover Strategy and Risk Assessments and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Review and comment on the Construction Strategy and the Health and Safety Strategy and provide recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Review and comment on the Project Execution Plan and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Review and comment on the Project Programme and the Project Budget and provide recoomendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Comment on and review the Information Exchange, preliminary Cost Information, Project Strategies and Final Project Brief and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Review and comment on the performance of the Project Team and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.10 | Review proposals for the selection of one or more specialists, to provide input into the Concept Design and provide recommendation to the Contracting Authority in consultation with the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.11 | Review, comment and provide recommendations to the Contracting Authority on the selection methodology for the list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.12 | Review, comment and provide recommendations to the Contracting Authority on the preparation of the tender documentation including the Employer's Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.13 | Review, comment and provide recommendations in respect of the assessment of tenders and the tender report. |  | ✓ |  | ✓ | ✓ | ✓
4.14 | Review, comment and provide recommendations to the Contracting Authority in respect of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Review and comment on the preparation and progress of the Developed Design, Site Information, Project Information, Cost Information and Project Strategies and provide updates and recommendations to the Contracting Authority. | ✓ |  | ✓
5.2 | Review and comment on the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Review and comment on the Handover Strategy and Risk Assessments and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Review and comment on the Construction Strategy and the Health and Safety Strategy and provide recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Review and comment on the Project Execution Plan and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Review and comment on the Project Programme and the Project Budget and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Review and comment on the Information Exchange and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Review and comment on the performance of the Project Team and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.10 | Review proposals for the selection of one or more specialists, to provide input into the Developed Design and make recommendation to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.11 | Review, comment and provide recommendations to the Contracting Authority on the selection methodology for the list of tenderers. | ✓
5.12 | Review, comment and provide recommendations to the Contracting Authority on the preparation of the tender documentation including the Employer's Requirements. | ✓
5.14 | Review, comment and provide recommendations in respect of the assessment of tenders and the tender report. | ✓
5.15 | Review, comment and provide recommendations to the Contracting Authority in respect of the contract documentation (for pre-construction activities). | ✓
5.16 | Review, comment and provide recommendations to the Contracting Authority arising from the assessment of the submission from the selected tenderer of designs and specifications, pricing information and cash-flows, health and safety information, programmes and method statements etc (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Review and comment on the preparation and progress of the Technical Design, Site Information, Project Information and Cost Information and provide updates and recommendations to the Contracting Authority. |  |  | ✓
6.2 | Review and comment on the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Review and comment on the Handover Strategy and Risk Assessments and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Review and comment on the Construction Strategy and the Health and Safety Strategy and provide recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Review and comment on the Project Execution Plan and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Review and comment on the Project Programme and the Project Budget and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Review and comment on the Information Exchange and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Review and comment on the performance of the Project Team and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Review proposals for the selection of one or more specialists, to provide input into the Technical Design and provide recommendations to the Contracting Authority in consultation with the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.1 | Review, comment and provide recommendations to the Contracting Authority on the selection methodology for the list of tenderers. |  |  | ✓
6.11 | Review, comment and provide recommendations to the Contracting Authority on the preparation of the tender documentation including the Employer's Requirements. |  |  | ✓
6.12 | Review, comment and provide recommendations in respect of the assessment of tenders and the tender report. |  |  | ✓
6.13 | Review, comment and provide recommendations to the Contracting Authority in respect of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.14 | Review, comment and provide recommendations to the Contracting Authority arising from the assessment of the submission from the selected tenderer of designs and specifications, pricing information and cash-flows, health and safety information, programmes and method statements etc to ensure alignment with the contract documentation (for pre-construction activities). | ✓ | ✓ |  | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Review construction conformance with the contract documentation and Construction Programme and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Review design development, health and safety performance, cash-flow and progress of the project and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Review and comment on the Sustainability Strategy and the Sustainability Checkpoint and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Review and comment on the Handover Strategy and Risk Assessments and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Review and comment on the Construction Strategy and the Health and Safety Strategy and provide recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Review and comment on the Project Programme and the Project Budget and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Review and comment on the Information Exchange and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Review and comment and monitor preparation and progress of the Project Information and the As Constucted Information and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Review and comment and monitor preparation and progress of the implementation of the Handover Strategy and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.10 | Review and comment on the planned maintenance programme and the recommendation on the procurement of the planned maintenance and make recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Review and comment on the performance of the Project Team and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Review proposals for the selection of one or more specialists, to provide input into the Design during Construction and provide recommendations to the Contracting Authority in consultation with the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Review, comment and provide recommendations to the Contracting Authority arising from the assessment of the submission from the selected tenderer of designs and specifications, pricing information and cash-flows, health and safety information, programmes and method statements etc to ensure alignment with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.14 | Review and comment on the progress of the preparation of the 'As Constructed' Information and provide updates and recommendationsto the Contracting Authority. |  |  | ✓
7a.1 | Review and comment on activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | In co-operation with the other members of the Project Team concerned, evaluate claims and make and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Review, comment and provide updates and recommendations to the Contracting Authority in respect of the handover of the building in accordance with the Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Review and comment on the defects list and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Review and comment on the progress of completion of tasks in accordance with the Handover Strategy and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Review and comment on the progress of completion of the update of the Project Information and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Review and comment on the progress of completion of the update of the 'As Constructed' Information and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Review and comment on the completion of the tasks in the Handover Strategy and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Review and comment on the Post Occupancy Evaluation and provide recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Review and comment on the update of 'As Constructed' information in accordance with Contracting Authority feedback and provide updates and recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Review and comment on the update of the Project information in accordance with Contracting Authority feedback and provide updates and recommendations to the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Review and comment on the post completion defect rectification process in accordance with GSL requirements and provide updates and recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Review and comment on the post completion monitoring process in accordance with GSL requirements and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Review and comment on the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects and provide recommendations to the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 8. Principal Designer
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 8 - Principal Designer
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority as defined in Regulation 11 and Regulation 12 of the CDM Regulations 2015. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | In consultation with the Project Lead, the Lead Designer and the Contracting Authority, prepare a programme for the 'pre-construction' phase to ensure all health and safety aspects arising from the project are effectively managed. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Manage the pre-construction process to ensure that all design, technical, organisational and programming aspects take into account the general principles of the prevention of health and safety risks and that this is reflected in the content of Health and Safety Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Monitor the pre-construction phase to ensure that, so far as is reasonably practicable, the project will be implemented and delivered without risks to health or safety. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Ensure that all suppliers cooperate with the Supplier, Contracting Authority and each other in respect of matters impacting health and safety. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Advise on health and safety considerations affecting or affected by procurement methods, approaches to design, construction, maintenance and operation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Ensure, as far as reasonably practicable, that the Project Team and the Contracting Authority and any other suppliers comply with their statutory duties under health and safety legislation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Ensure the Project Team work to reduce risks, coordinate information, and generate solutions for construction, maintenance and operation that are as risk free as possible. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Organise and ensure circulation of all pre-existing information (including Site Information and Project Information) for the Project to the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Ensure that coherent health and safety information is handed over to the Principal Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.13 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.14 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.15 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.16 | Participate in the Change Control Procedure and monitor Design development to assess the impact on health and safety in design, construction, maintenance and operation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.17 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide comments to the Project Lead and attend workshops to discuss the Business Case and to develop the Strategic Brief for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Review findings from post project evaluations from relevant projects and contribute to the Sustainability Checkpoint to inform the approach to the Strategic Definition for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.3 | Provide contributions to the Project Lead to establish the Project Brief, the Initial Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.4 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Liaise with the Project Team and the Contracting Authority to obtain copies of all available Site information including maps, plans, surveys, reports or other documentation relating to the project and any adjacent areas. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Receive the existing health and safety file and Site Information, where available, from the Contracting Authority and advise upon its adequacy for the project. Update the existing health and safety file for use in connection with the Project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Lead and manage the contribution in respect of health and safety considerations to the development of the Initial Project Brief. The Initial Project Brief shall include Project Objectives, Quality Objectives, Project Outcomes, environmental performance/Sustainability Aspirations, Project Budget and Project Programme and all other parameters, risks and/or constraints. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Review Site Information and Project Information and provide comments and attend workshops, as required, to develop the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Provide comment for the development of the Project Roles Table and Contractual Tree. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Provide comment to the Project Lead and Lead Designer to prepare the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Lead and manage the health and safety implications contribution to the preparation of option appraisals that meet the Initial Project Brief. Options produced by the Project Team should collectively address: - Built Form: including building size, shape, orientation, sub-division, shading, weather and noise protection etc. - Construction standards: including floor load capacities, column to column spans, insulation, fire protection, glazing ratios, thermal and noise insulation, thermal capacity, natural and artificial illumination, ventilation etc. - Structural and hard surfacing materials, foundations, temporary structures etc: - Engineering Services and components: including heating, hot water, cooling, ventilation, lighting, communications, lifting or transportation equipment and public health systems etc.; their operational relationships, methods of control and means of energy supply, distribution and recovery etc. - Foul and surface water drainage, attenuation and rainwater harvesting - External paving and surfacing, roads, car parks and footpaths | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.8 | Lead and manage the health and safety implcations contribution to the preparation of the Feasibility Study for the Contracting Authority preferred option(s) | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.9 | Review and contribute to the update the Project Programme. Lead and manage the update of the health and safety information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.10 | Contribute to the preparation of the Handover Strategy and undertake the review of Risk Assessments in preparation for the Concept Design stage and contribute to the Sustainability Checkpoint and the development of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.11 | Assist in the selection one or more specialists, where appropriate and legally compliant, to provide input into option appraisals and/or the Feasibility Study in consultation with the Contracting Authority and the Project Team. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.12 | Prepare a health and safety file for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Ensure that all persons working in relation to the pre-construction phase cooperate with the Contracting Authority, the Supplier and each other. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Incorporate the agreed changes to the Concept Design, Site Information and Project Information into the update of the health and safety information in accordance with the Change Control Procedure and the Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Contribute to the development of the Sustainability Strategy, the Maintenance and Operational Strategy and the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Contribute to the development of the Handover Strategy and review and comment on Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Contribute to the Construction Strategy and lead and manage the update and development of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.6 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.7 | Contribute to the review and update of the Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.8 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.9 | Ensure all designers comply with their duties in Regulation 9 of the CDM Regulations 2015.. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.10 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.11 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.12 | Contribute to the preparation of the tender documentation |  | ✓ |  | ✓ | ✓ | ✓
4.13 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the health and safety proposals in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.14 | Assist in the agreement and the finalisation of the detailed content of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Ensure that all design, technical, organisational and programming aspects take into account the general principles of prevention of health and safety risks and, where relevant, the content of any construction phase plan shall adopt these general principles. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Incorporate the agreed changes to the Developed Design, Site Information and Project Information into the update of the health and safety information in accordance with the Change Control Procedure, the Design Responsibility Matrix, Information Exchanges and the Design Programme. Contribute to the development of Project Strategies. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Contribute to the review and update of the Construction Strategy and lead the review and update of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.6 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.7 | Contribute to the review and update of the Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.8 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.9 | Ensure all designers comply with their duties in Regulation 9 of the CDM Regulations 2015. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.10 | Contribute to the selection of a list of tenderers. | ✓
5.11 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.12 | Contribute to the preparation of the tender documentation | ✓
5.13 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the health and safety proposals in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.14 | Assist in the agreement of the detailed content and finalisation of the contract documentation (for pre-construction activities) | ✓
5.15 | Lead the assessment of the health and safety impact of submissions from the selected tenderer of designs and specifications, and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Ensure that all design, technical, organisational and programming aspects take into account the general principles of prevention of health and safety risks and, where relevant, the content of any construction phase plan shall adopt these general principles. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.2 | Incorporate the agreed changes to the Technical Design, Site Information and Project Information into the update of the health and safety information in accordance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Contribute to the review and update of the Sustainability Strategy and the Maintenance and Operational Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Contribute to the review and update of the Handover Strategy and review and update Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Contribute to the review and update of the Construction Strategy and lead the review and update of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.6 | Contribute to the review and update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.7 | Contribute to the review and update of the Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.8 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Ensure all designers comply with their duties in Regulation 9 of the CDM Regulations 2015.. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.10 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.11 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.12 | Contribute to the preparation of the tender documentation |  |  | ✓
6.13 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include the review and evaluation of the alignment of the health and safety proposals in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.14 | Assist in the agreement of the detailed content and finalisation of the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.15 | Lead the assessment of the health and safety impact of submissions from the selected tenderer of designs and specifications, and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Liaise with and share with the Principal Contractor information relevant to the planning, management and monitoring of the construction phase and the coordination of health and safety matters during the construction phase. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Assist the Principal Contractor to prepare the construction phase plan by providing the Principal Contractor with all information the Principal Designer holds that is relevant to the construction phase plan including— (a) pre-construction information obtained from the Contracting Authority; (b) any information obtained from designers under regulation 9(3)(b). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Contribute, as necessary, to the provision of information to the Contract Administrator to assist contract administration. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Contribute to the review and update of the Project Programme and the Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Contribute to the review and update of the Sustainability Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Contribute to the review and update of the Construction Strategy and lead the review and update of the Health and Safety Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Monitor the compilation of the 'As Constructed' Information is provided in accordance with the Construction Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Contribute to the implementation of the Handover Strategy | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Monitor and verify that agreed changes to the Design during Construction are implemented in compliance with the Change Control Procedure, Design Responsibility Matrix, Information Exchanges and the Design Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.10 | Comply with the Information Exchange requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.11 | Contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.12 | Lead the assessment of the health and safety impact of submissions from the selected tenderer of designs and specifications, and the further review and evaluation of responses to any clarifications from the tenderer. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.13 | Contribute to the preparation of the 'As Constructed' Information. |  |  | ✓
7a.1 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Assist the Principal Contractor in finalising the construction phase plan by providing to the Principal Contractor all information the Principal Designer holds that is relevant to the construction phase plan including— (a) pre-construction information obtained from the Contracting Authority; (b) any information obtained under regulation 9(3)(b). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Undertake the tasks in accordance with the Handover Strategy and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Contribute to the provision of information to the Contract Administrator to assist administration of the contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Contribute to the update of the Project Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Contribute to the update of the 'As Constructed' Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
Note: The services set out above are designed to comply with the Principal Designer duties as set out in the Construction (Design & Management) Regulations 2015 and do not cover the same range or scope of activieis described under the obsolete role of CDM Coodinator

## 9. Contract Admin
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 9 - Contract Administrator
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Establish and maintain contract administration procedures, hierarchy of responsibility and the Communication Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Where there is duplication between the Services provided by the Supplier and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Co-operate at all times with the Principal Designer in respect of the provision of information and Risk Asssessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Participate in the Change Control Procedures and monitor Design and Cost Information development against the Project Budget, Design Programme and Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.1 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Not Applicable
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Not Applicable
4 | RIBA Stage 2 - Concept Design
4.1 | Lead the agreement of the detailed content and finalise the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Lead the agreement of the detailed content and finalise the contract documentation (for pre-construction activities). | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Lead the agreement of the detailed content and finalise the contract documentation (for pre-construction activities). |  |  | ✓
7 | RIBA Stage 5 - Construction
7.1 | Administer the contract in accordance with the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Manage the Change Control Procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Visit the site as appropriate to inspect the progress of the project and the quality of materials, goods, equipment and workmanship in consultation with the Project Team to ascertain compliance with the contract documentation, Design Programme, Construction Programme and Project Budget. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Monitor and record the activities, labour levels, productivity, plant and equipment deployed and use thereof by the Contractor and its supply chain and the effect of any matters that are, or maybe, affecting the foregoing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Monitor the submission and approval of designs, specifications testing and commissioning by the Contractor and its supply chain. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Co-ordinate, arrange and chair meetings on site, as may be necessary, with the Project Team to establish progress of the project and compliance of the project with the contract documentation and all relevant Programmes and Budgets. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.7 | Provide monthly progress reports to the Contracting Authority in respect of the above and provide early warning of any decisions by the Contracting Authority which may be required in the following eight weeks. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.8 | Provide opinion, instructions and certifications for the proper execution of the Project in accordance with the contract documentation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.9 | Check, agree and approve as appropriate the expenditure of provisional sums and the Contractor’s applications for interim payment.
7a.1 | In collaboration with the other suppliers, assess any compensation events/ financial claims/ applications for extension of the completion date and the effects on the programme of any proposed variations, and monitor the cost and programme effects of any variations for which instructions are issued to the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.3 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | At Practical Completion, co-ordinate handover and see that all appropriate commissioning inspections and tests are complete and contribute to the Sustainability Checkpoint. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Organise, attend the site and record all matters relating to handover of the project, and each and any section and part thereof, in accordance with the Handover Strategy, in accordance with the Building Contract including:- - Arranging and co-ordinating pre-handover inspections by other suppliers and carrying out handover inspections and reporting to the parties to the building contract in writing as to defects requiring rectification before handover; - Carrying out further handover inspections as required and certifying to the Contracting Authority in writing as soon as the project, and/or each and any section and part thereof, has reached completion and is ready for handover. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Advise on the resolution of defects. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.4 | Oversee the compilation of handover documentation in accordance with the Handover Strategy including ‘As Constructed’ Information. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.5 | Issue the final statement, or equivalent, on conclusion of the agreement of the final account, or equivalent, and the rectification of all defects in accordance with the the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.6 | Conclude administration of the Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Contribute to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 10. BIM IM updated
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 10 - BIM Information Manager
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend regular meetings in respect of Design, consult and liaise with the Lead Designer in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Identify activities to be undertaken and responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake and take responsibility for actions to be undertaken by the BIM Information Manager. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Monitor that Design is in accordance with the Technology Strategy. Review, develop and update the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Establish rigorous procedures to monitor the production of Design information is in accordance with the Technology Strategy in order that any shortcomings and/or queries are immediately highlighted and rectified in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy, Design Programme and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Establish a Common Data Environment including processes and procedures to enable reliable information exchange between Project Team Members, the Contracting Authority and other parties. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Manage Common Data Environment processes and procedures, validate compliance with them and advise on non-compliance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Establish, agree and implement the information structure and maintenance standards for the Information Model. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Receive information into the Information Model in compliance with agreed processes and procedures. Validate compliance with information requirements and advise on non-compliance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Maintain the Information Model to meet integrity and security standards in compliance with the employer’s information requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Initiate, agree and implement the Project Information Plan and Asset Information Plan covering: - information structure across roles e.g. software platforms (all levels of supply chain) appropriate to meet the Employer requirements and Project Team resources - responsibility for provision of information at each Stage - level of detail of information required for specific Project Outputs e.g. planning, rocurement, FM procurement - the process for incorporating As Constructed, testing, validation and commissioning information to enable integration of information within the Project Team and co-ordination of information by the Lead Designer | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Agree the formats for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Support the implementation of the Project BIM protocol and the Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.13 | Assist the Project Team Members to establish Information Exchange processes, including the definition and agreement of procedures for convening, chairing, attendance and responsibility for recording “Information Exchange process meetings" | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.14 | Establish and implement record keeping, archiving and audit trail for the Information Model | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.15 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers and in accordance with the Schedule of Services for each, the Project Roles Table, the Design Responsibility Matrix and the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.16 | Where there is duplication between the Services provided by the Supplier under the term and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.17 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.18 | Co-operate at all times with the Principal Designer in respect of the provision of Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.19 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.20 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.21 | Comply with the project management procedures, hierarchy of responsibility, the Communication Strategy and the exchange of information both informally and formally at Information Exchanges. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.22 | Participate in the Change Control Procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.23 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1a.1 | Host the Common Data Environment | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Review findings from post project evaluations from relevant projects to inform the approach to the Strategic Definition for the project. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2.2 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Contribute to the agreement of the procurement route and the standard form of Building Contract. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Contribute to the development of the Project Roles Table and Contractual Tree by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Continue to support the implementation of the Project BIM protocol and the update of the Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.6 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.7 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Contribute to the review and update of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.3 | Continue to support the implementation of the Project BIM protocol. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.6 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.7 | Contribute to the preparation of the tender documentation |  | ✓ |  | ✓ | ✓ | ✓
4.8 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.9 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
4.10 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Contribute to the review and update of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Continue to support the implementation of the Project BIM protocol. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.5 | Contribute to the selection of a list of tenderers. | ✓
5.6 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.7 | Contribute to the preparation of the tender documentation. | ✓
5.8 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.9 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.10 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
5.11 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.2 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Continue to support the implementation of the Project BIM protocol. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.5 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.6 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.7 | Contribute to the preparation of the tender documentation |  |  | ✓
6.8 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.9 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.10 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
6.11 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Contribute to the review and update of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Continue to support the implementation of the Project BIM protocol. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.5 | Contribute to the preparation of a planned maintenance programme for the project, post handover, and contribute to recommendations for the procurement of the planned maintenance. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.6 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.1 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Continue to support the implementation of the Project BIM protocol. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of As Constructed information in accordance with Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL. requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Manage the contribution in respect of design to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓

## 11. BIM Co-Ord updated
Schedule of Services (By Procurement Type)
Project Management & Full Design Team Services Procurement - RM3741
Core Service Discipline 11 - BIM Co-Ordinator
Ref | Scope of Services | Procurement Type
|  | D&B (Single) | D&B (2 Stage) | Traditional | 2 Stage Open Book | Cost Led Procurement | Integrated Project Ins
1 | General Services
1.1 | Provide the Services for all Workplan stages unless instructed otherwise by the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.2 | Attend regular meetings in respect of Design, consult and liaise with the Lead Designer in the preparation of the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Identify activities to be undertaken and responsibility for the activities in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy and Design Programme. Undertake and take responsibility for actions to be undertaken by the BIM Co-ordinator. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.3 | Develop, implement and maintain the BIM Protocol for the project and establish and implement robust quality control and collaboration procedures to ensure that all models and datasets are accurate and that the level of information is fit for purpose.. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.4 | Establish rigorous procedures to monitor the production of Design information is in accordance with the BIM Protocol in order that any shortcomings and/or queries are immediately highlighted and rectified in accordance with the Project Roles Table, Design Responsibility Matrix, Technology Strategy, Design Programme and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.5 | Ensure that all stakeholders understand the BIM process and their role within it including BIM development, standards, data requirements etc. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.6 | Identify, document and resolve clashes using clash detection software. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.7 | Co-ordinate the data modelling and management process including liason with all Project Team Members and the Contracting Authority. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.8 | Consult and liaise with other suppliers on the Project Team to ensure that the Services provided by the Supplier are fully coordinated with the services provided by those suppliers and in accordance with the Schedule of Services for each, the Project Roles Table, the Design Responsibility Matrix and the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.9 | Where there is duplication between the Services provided by the Supplier under the term and the services of another supplier(s), the Supplier shall assist the Project Lead to resolve the service duplication by agreement with the supplier(s) concerned. The Supplier shall implement the actions the Project Lead confirms in writing. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.10 | Participate in the operation of an Early Warning System. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.11 | Co-operate at all times with the Principal Designer in respect of the provision of Risk Assessments. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.12 | Attend meetings with the Contracting Authority, Project Lead, other suppliers and the Contractor as necessary. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.13 | Attend and contribute to workshops and exercises with other suppliers to carry out value engineering, value management, environmental performance improvement initiatives and risk management. Contribute to recommendations for Contracting Authority approval based on the results of these exercises to deliver the best overall value for money. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.14 | Comply with the project management procedures, hierarchy of responsibility, the Communication Strategy and the exchange of information both informally and formally at Information Exchanges. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.15 | Participate in the Change Control Procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
1.16 | Work closely with the Contracting Authority, other suppliers and all stakeholders to foster a partnering culture. The culture will embody the principles of mutual trust and co-operation with an overall aim of delivering a successful project to the Project Brief, Project Budget and the Project Programme. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
2 | RIBA Stage 0 - Strategic Definition
2.1 | Provide contributions to the Project Lead to draft the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3 | RIBA Stage 1 - Preparation & Brief
3.1 | Contribute to the development of the Project Roles Table and Contractual Tree by the Project Lead. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.2 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy for the Initial Project Brief. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.3 | Review and update the Project BIM Protocol and Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
3.5 | Monitor and review conformance of Project Outputs with the BIM Protocol and the qualiy control and collaboration procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4 | RIBA Stage 2 - Concept Design
4.1 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.2 | Review and update the Project BIM Protocol and Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.4 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
4.5 | Contribute to the selection of a list of tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.6 | Contribute to the preparation of the Employer’s Requirements. |  | ✓ |  | ✓ | ✓ | ✓
4.7 | Contribute to the preparation of the tender documentation |  | ✓ |  | ✓ | ✓ | ✓
4.8 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  | ✓ |  | ✓ | ✓ | ✓
4.9 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). |  | ✓ |  | ✓ | ✓ | ✓
4.10 | Monitor and review conformance of Project Outputs with the BIM Protocol and the qualiy control and collaboration procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5 | RIBA Stage 3 - Developed Design
5.1 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.2 | Review and update the Project BIM Protocol and Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.3 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
5.4 | Contribute to the selection of a list of tenderers. | ✓
5.5 | Contribute to the preparation of the Employer’s Requirements. | ✓
5.6 | Contribute to the preparation of the tender documentation. | ✓
5.7 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. | ✓
5.8 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓
5.9 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. |  | ✓ |  | ✓ | ✓ | ✓
5.10 | Monitor and review conformance of Project Outputs with the BIM Protocol and the qualiy control and collaboration procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6 | RIBA Stage 4 - Technical Design
6.1 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.2 | Review and update the Project BIM Protocol and Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.3 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.4 | Contribute to the selection of a list of tenderers. |  |  | ✓
6.5 | Contribute to the preparation of the Employer’s Requirements. |  |  | ✓
6.6 | Contribute to the preparation of the tender documentation |  |  | ✓
6.7 | Contribute to the assessment of tenders and the preparation of the tender report. The assessment should include leading the review and evaluation of the alignment of the design and specification in each of the Contractor's Proposals with the Employer's Requirements set out in the tender documentation and the further review and evaluation of responses to any clarifications from the tenderers. |  |  | ✓
6.8 | Assist in the agreement of the detailed content and the finalisation of the contract documentation (for pre-construction activities). | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
6.9 | Contribute to the assessment of the submission from the selected tenderer of designs and specifications, to ensure alignment with the contract documentation and the further review and evaluation of responses to any Design Queries, clarifications etc from the tenderer. | ✓ | ✓ |  | ✓ | ✓ | ✓
6.10 | Monitor and review conformance of Project Outputs with the BIM Protocol and the qualiy control and collaboration procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7 | RIBA Stage 5 - Construction
7.1 | Contribute to the preparation of the Design Responsibility Matrix, Information Exchange and Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.2 | Review and update the Project BIM Protocol and Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.3 | Review and contribute to the update of the Project Execution Plan. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7.4 | Monitor and review conformance of Project Outputs with the BIM Protocol and the qualiy control and collaboration procedures. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.1 | Assist the Contract Administrator with all activities in connection with the adjudication of disputes between the Contracting Authority and the Contractor. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
7a.2 | In co-operation with the other members of the Project Team concerned, evaluate claims and make recommendations. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8 | RIBA Stage 6 - Handover & Close-Out
8.1 | Assist Project Team Members to assemble information for Project Outputs | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.2 | Continue to support the implementation of the Project BIM protocol and update the Appendices | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
8.3 | Monitor and review conformance of Project Outputs with the Technology Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9 | RIBA Stage 7 - In-Use
9.1 | Undertake the tasks listed in the Handover Strategy. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.2 | Contribute to the Post Occupancy Evaluation. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.3 | Contribute to the update of 'As Constructed' information in accordance with Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.4 | Contribute to the update of Project Information in response to ongoing Contracting Authority Feedback. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.5 | Contribute to the post completion defect rectification process in accordance with GSL. requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.6 | Manage the contribution in respect of design to the post completion monitoring process in accordance with GSL requirements. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓
9.7 | Contribute to the review of Project Performance, Project Outcomes, the Sustainability Checkpoint and the outcome of any research and development aspects. | ✓ | ✓ | ✓ | ✓ | ✓ | ✓